## 2021-22
2021 - 22 Complaints action list (snapshot taken September 2022, personal identifiers removed)
Team/Dept | Date of complaint | Contact Ref No. | Action required | Status | Due date | Comments | Reported to Performance Committee? | Reported to tenants? By what method(s)
Housing Services | 2021-05-05 | 867965 | Reminder/Customer Service training around the importance of customer call backs within a reasonable timescale | in progress | E-mail reminder by 30/05. Training by Autumn 21 | Important that team are reminded on a regular basis of the importance of calling customers back. | y | Annual report on website
Housing Services | 2021-06-16 | 875996 | Remind staff of frontline resolution process and ensure actions are being completed by patch officer or the team leader. | Complete | Cover in staff 1 to 1 meetings, Aug 2021. |  | y | Annual report on website
Housing Services | 2021-06-21 | 877048 | Suggest the Association provides advice leaflet regarding seagulls nesting and publishes advice on the Website and Facebook. Request that we look at possible deterrents to stop seagulls nesting in the future. | Complete | By Autumn 2021. | E-mailed staff, given links to information on local authority websites. No budget available for deterrents or nest removal. | y | Annual report on website
Housing Services | 2021-07-28 | 883158 | Remind all staff visiting schemes to log scheme visits on the notice boards so tenants can see the schemes are being regularly checked. | Complete e-mail sent. | By October 2021. |  | y | Annual report on website
Housing Services | May/June 21 | Various | Number of complaints about overgrown gardens following delay to new contractors starting. Work was caught up but suggest keeping tenants informed of delay in Realtime by providing update on website/social media | Complete | By Autumn 2021. | E-mail to Manager advising that in hindsight it would have been good to proactively keep tenants informed and to consider that should there be similar issues in the future. | y | Annual report on website
Customer Service | 2021-08-01 | Various | Review of hybrid arrangements to allow call handling to be more closely monitored | Complete | 2021-08-01 | Changes agreed with staff and implemented with immediate effect | y | Annual report on website
Customer Service | 2021-08-01 | Various | Customer Services Manager appointed with remit to improve customer service. Calls to be closely monitored, audited and learning items to be used for coaching staff at 1-1s | Complete | ongoing |  | y | Annual report on website
Housing/Property | 2021-09-01 | 890619 | Complaint not upheld but review required around the use of storage cupboards/spaces in schemes. Appears to be a mixed approach depending on the schemes. | In progress | 2022-02-01 |  | y | Annual report on website
Property | 2021-10-01 | 895794 | Master key letters for tenant safety inspections are being reviewed as part of a wider review of master key procedure. Need to strike the right balance between the importance of obtaining access versus not wanting to distress tenants. | In progress | 2022-05-01 |  | y | Annual report on website
Property | Various in Q3 | Various | Tenants waiting too long after reporting repair to get pre-inspection, which delays work. Pre-inspection procedure is currently being reviewed (as part of the project to move repairs calls to Customer Service team) to ensure pre-inspection is tied to order number wherever possible (pre-inspection time should be counted within overall order time but currently isn't) | Complete | 2022-04-15 |  | y | Annual report on website
Property | Various in Q3 | Various | Repairs are often taking too long to be completed. Procedure required to ensure that overdue repairs are being chased an officers to receive patch report for their area. This is being further considered as part of the process of moving repairs calls to Customer Service team. | Complete | 2022-04-01 | Patch reports on overdue orders issued to Officers 14/02/2022 | y | Annual report on website
Property | Various in Q3 | Various | As above, need to chase overdue repairs - currently 3 automated emails go out to contractors - one just before due date is reached and one just after. Review of the automation settings show that they need updated as they relate to staff who have left LHA. Additional automated email being added to chase five days after repair date. | Complete | 2022-03-01 | This will be an ongoing process | y | Annual report on website
Property | Various in Q3 | Various | Reminder/Customer Service training around the importance of customer call backs within a reasonable timescale. Team Leader to regularly review team workflows and raise issues with staff if call-backs not being completed. | Complete | E-mail reminder by 01/03 Training by May 2022 | Bi-weekly meetings will also be arranged to discuss with patch officers alongside chasing of outstanding repairs | y | Annual report on website
Property | Various in Q3 | Various | Various tenants complained that they were being kept up to date when repairs were delayed or parts were needed. Customer Service training to be arranged for Officers to ensure everyone understands the importance of regular contact with tenants. | Complete | 2022-04-01 | This will require ongoing reminders | y | Annual report on website
Property | Various in Q3 | Various | A few of the complaints had been closed off without comment or with vague closing remarks that didn't say what action was to be taken. Team to be reminded of importance of detailed comments in QL | Complete | 2022-03-01 |  | y | Annual report on website
Property | Various in Q3 | Various | A number of complaints related to repair quality. Automated post-inspection process being set up in QL to ensure 10% of repairs are post-inspected. | Complete | 2022-04-01 | 10% post inspection process implemented | y | Annual report on website
Property | 2021-12-10 | 908144 | Staff are not clear on process for providing a disabled parking space to tenants. Simple guidance note to be drafted. |  | 2022-05-01 |  | y | Annual report on website
Property | 2021-12-06 | 907283 | Complaint was closed off as 'resolved' but only partially dealt with. Complaint relating to street lighting was not resolved and order for repair was not issued until Feb 2022. Team to be reminded not to close off repairs if only partially resolved | Complete | 2022-03-01 |  | y | Annual report on website
Housing | 2022-03-08 | 923368 | Applicant unhappy about communication around when flat he had been offered would be ready to let. He thought only minor repairs outstanding but staff member he spoke to unsure. Was willing to take flat if only minor repairs and could be resolved post occupation. | Complete | 2021-03-08 | E-mails to Housing and Property Team Leader for follow up about communication between teams. Also Property Officer not aware that minor repairs can be done post occupation and follow up with Housing Assistant to be done by TL about personal communication. |  | Annual report on website
Property | 2022-01-24 | 914100 | Reminder to staff of the importance of calling tenants back. In this case the customer had phoned four times to get a response | in progress | 2022-08-01 | This will be an ongoing reminder to staff at team meeting |  | Annual report on website
Property | 2022-02-15 | 919005 | Clear instructions to contractor issued of whom requests for new boilers and failure reports should be sent to | Completed | 2022-06-23 | Contractor advised several weeks ago of contract email groups for Association staff and what they should be used for |  | Annual report on website
Property | 2022-03-07 | 922775 | More proactive action taken to prevent repeat visits getting repairs completed. Interaction with contractor to establish issues and resolve them. Customer to be kept updated on action taken. | in progress | 2022-08-01 | Officers need to be aware if repairs issues are ongoing and not being resolved timeously |  | Annual report on website
Property | 2022-03-28 | 926113 | Customer should have been kept up to date on action being taken if any delay in obtaining quotes | in progress | 2022-08-01 | Team needs to be aware of keeping people informed |  | Annual report on website